BUSHWICK DAILY

Intern Project · Summer 2026

The Bushwick Grocery Price Index

Project Brief & Playbook

| Assignment | Pitch, plan, report, and publish a data-journalism grocery price index |
| --- | --- |
| Team | 2 interns (rising HS seniors) + Intern Coordinator + Editor/Orchestrator |
| Window | Tue Jul 7 to Wed Jul 15, 2026 (one week) |
| Deliverable | One published data story on bushwickdaily.com + social package |

# 1 · The Project in One Page

What you're making. A grocery price index: you pick a fixed "basket" of everyday grocery items, then go store to store and record what that exact same basket costs at each one. The result is a clear, sourced comparison of where groceries are cheapest and most expensive across Bushwick, Ridgewood, and the surrounding area. Bushwick Daily ran versions of this in 2017 and 2021.

Why it matters right now. Grocery affordability is one of the biggest local stories of the year. NYC food prices have climbed far faster than the national average, Mayor Mamdani is building city-owned grocery stores around a "core basket of staples," and Amazon is reshaping the grocery landscape (closing its Fresh/Go stores, expanding Whole Foods, and pushing same-day delivery). Your index puts local numbers behind that conversation.

How you'll do it. You'll move through nine phases: research, pitch, methodology, data collection, analysis, follow-up reporting, writing, social, and publishing. Each phase has its own template with fields to fill in, so you always know exactly what's expected. You submit each phase to the shared Google Drive folder; the Editor reviews and approves before you move on. In the field, you'll log every price and snap a photo of the product and its price tag through a Google Form on your phone.

What the finished piece needs. A fair, transparent comparison a reader can trust: the same items measured the same way at every store, every number traceable to a photo and a spreadsheet row, real voices (a store owner, an economist) explaining why prices differ, and a clear takeaway. This assignment walks you through every step of producing and publishing a data-journalism piece, from first research to final promotion.

The index only works if it's consistent: the same basket, the same rules, the same week, at every store. Every standard in Section 4 protects that consistency.

# 2 · How This Works

### Your roles

- Interns (both of you): do the research, reporting, data collection, analysis, writing, and social. Split the work but review each other's.

- Intern Coordinator: teaches each phase (how to research, how to build a pitch, how to design a fair method, how to write it up), unblocks you, and checks work before it goes to the Editor.

- Editor / Orchestrator: reviews each submitted deliverable, approves or sends it back, and does the final edit before publishing.

### The submit-and-review loop

Every phase works the same way: (1) open that phase's template, (2) fill in the fields, (3) save it into the matching phase folder in the shared Drive, (4) mark the row "Submitted" in the Master Tracker, (5) the Coordinator reviews, then the Editor approves. You don't start the next phase until the current one is approved, especially the pitch and the methodology. Getting sign-off before moving forward is standard newsroom practice.

### The shared Google Drive folder

Everything lives in one shared Drive folder, divided by phase. Create it exactly like this and share it with the Coordinator and both interns:

| Folder | What goes in it |
| --- | --- |
| 00_START_HERE | This Playbook + the Master Tracker (open these first) |
| 01_Research | Research Brief |
| 02_Pitch | Story Pitch |
| 03_Methodology_and_Plan | Methodology & Field Plan (basket + store list live in the Tracker) |
| 04_Data_Collection | Price Submission Form, the Price Data sheet it feeds, and a Photos subfolder |
| 05_Analysis_and_Findings | Findings Memo (analysis math lives in the Tracker) |
| 06_Reporting_and_Interviews | Source & Interview Log |
| 07_Writing | Article Draft |
| 08_Social_and_Promotion | Social & Promotion Package |
| 09_Publish_and_Handoff | Final published link, screenshots, and the project retro |

Uploading the templates:  the templates are Word (.docx) and the tracker is Excel (.xlsx). Drag them into Drive, then right-click, choose Open with, then Google Docs or Google Sheets to edit them as normal Google files (or turn on the "Convert uploads" setting first). They're built to convert cleanly.

# 3 · The Pipeline at a Glance

Nine phases from blank page to published story. Each "deliverable" is its own template with fill-in fields.

| Phase | You produce | Approved by |
| --- | --- | --- |
| 1 · Research & Context | Research Brief | Coordinator |
| 2 · Pitch | Story Pitch | Editor |
| 3 · Methodology & Plan | Methodology & Field Plan (+ locked basket & store list) | Editor |
| 4 · Data Collection | Completed Price Data sheet + photos (via the Form) | Coordinator |
| 5 · Analysis & Findings | Findings Memo (+ basket totals & index) | Coordinator |
| 6 · Reporting & Interviews | Source & Interview Log (quotes + fact-checks) | Coordinator |
| 7 · Writing | Article Draft | Editor |
| 8 · Social & Promotion | Social & Promotion Package | Editor |
| 9 · Publish & Handoff | Published story + posts + retro | Editor |

# 4 · Data Standards You Can't Skip

These rules separate a trustworthy index from a random list of prices. Read them before you design your method; they're built into the Phase 3 template.

### 1. Standardize every item (brand, size, unit)

A price only means something if it's the same thing everywhere. For each basket item, lock a specification before you go out: a brand rule, a size, and how you'll price it. "Milk" is not comparable; "half-gallon of 2% store-brand milk" is. When the 2017 index ran into this, the reporters had to sort out pint-vs-quart half-and-half. Decide those rules up front.

### 2. Record which kind of price it is

For every item log whether the price is the regular shelf price, a sale price, a loyalty/members-only price, or a unit price. Sales distort comparisons (our 2017 piece flagged this). Use the regular shelf price as your primary basket number; log sale/loyalty prices separately so you can talk about them without skewing the index.

### 3. Define your index

Decide exactly what "the index" is. Baseline recommendation: (a) the total cost of the full basket at each store, and (b) each store scored against the cheapest store = 100 (so a store at 130 is 30% more expensive than the cheapest). Optionally add per-category sub-indexes (produce, dairy, pantry, protein). Write your definition down. A table of prices is not an index until you've defined the comparison.

### 4. Collect within a tight window

Prices move week to week, so gather the whole comparison basket across as few days as possible and always record the date and time of each price. If a store is priced a week later than the rest, note it.

### 5. Handle missing items and substitutions

If your exact spec isn't in stock, either (a) record the closest substitute and clearly flag it, or (b) mark the item N/A at that store. Agree the substitution rule in advance so both of you do it the same way. Never quietly swap in a different size or brand.

### 6. Photo protocol in the store

Two photos per item: the product and its price tag or shelf label. Some stores restrict photography. Be quick and unobtrusive; if a staffer asks, say you're a Bushwick Daily intern and ask if it's okay. If photos aren't allowed, write down the price and the shelf-tag details instead. Upload photos the same day.

### 7. Everything traces back

Every price in the final article must trace to a row in the Price Data sheet and a photo. Every quote must trace to a named source. The Phase 7 template has a fact-check checklist; nothing publishes until each number and quote is confirmed.

On the beer item:  one legacy basket item is a specific beer (Six Point Sweet Action). You may be under 21, so do not buy alcohol. Photograph the shelf price tag only, or drop the item and note why.

# 5 · Day-by-Day Timeline (Jul 7-15)

This is a tight schedule that works if you keep moving. The biggest risk is interview response time, so start reaching out to sources by Day 5 at the latest.

| Day | Focus | Produce / submit |
| --- | --- | --- |
| Day 1 · Tue 7/7 | Kickoff + research. Read the 3 prior BD pieces; research the Mamdani plan + Amazon/Whole Foods; find 2-3 comparable price-index articles elsewhere. Coordinator lesson: scoping a story & finding prior art. | Start Research Brief |
| Day 2 · Wed 7/8 | Finish research; write the pitch. Coordinator lesson: what makes a pitch (hook, thesis, sourcing, why now). | Submit Research Brief + Pitch; Editor approves pitch |
| Day 3 · Thu 7/9 | Lock methodology: basket + standardization rules, store list + map + tiers, roles, delivery-app decision. Coordinator lesson: fair method & sampling. | Submit Methodology & Field Plan; Editor approves |
| Day 4 · Fri 7/10 | Field collection A: hit ~half the stores; log via the Form as you go. Check the Coverage Matrix that evening. | Price Data filling in |
| Weekend · Sat-Sun 7/11-12 | Field collection B / buffer: finish remaining stores + delivery-app prices if in scope. Keep the window tight; record dates. | Price Data complete |
| Day 5 · Mon 7/13 | Analysis + findings; start source outreach (owners, economists). Coordinator lesson: signal vs. noise in data. | Submit Findings Memo |
| Day 6 · Tue 7/14 | Interviews + write. Coordinator lesson: structuring a data story + fact-checking. | Submit Article Draft; Editor edits |
| Day 7 · Wed 7/15 | Revisions + build charts/map + social package; run the publish checklist; publish + post + send boost DMs. | Publish + Social Package |

# 6 · Story Context

You'll do your own research in Phase 1 and verify all of this yourselves, since details change. Here's the landscape to build from. Treat every claim below as something to confirm and cite.

### Prior Bushwick Daily coverage (read these first)

- 2017: "Reality Check: We Compared the Prices in 9 Grocery Stores in Bushwick & Vicinity." A full basket priced across 9 stores. This is the closest model for what you're doing. bushwickdaily.com/guides/4535-ultimate-guide-to-grocery-shopping-bushwick/

- 2021: "We Compared the Bushwick Area's Grocery Stores So You Don't Have To." Store-by-store ratings + a smaller cart; it linked an interactive data viz. bushwickdaily.com/guides/bushwick-ridgewood-supermarkets-grocery-stores/

- "Whole Foods Is Coming to Bushwick." Context for the premium / national-chain angle. bushwickdaily.com/news/whole-foods-is-coming-to-bushwick/

### The policy backdrop

- Mamdani's city-owned grocery stores. A central promise of the mayor: five municipal stores (one per borough) built around keeping a core basket of staples cheap. The first identified site is La Marqueta in East Harlem; a Brooklyn site is still being examined. Under the model, the city owns the land and covers overhead while a private operator runs the store and passes savings on to shoppers for core staples. Local hook: Councilmember Jennifer Gutiérrez (D-Brooklyn, whose district includes the Bushwick area) has pushed to make the program permanent. Your basket is essentially a real-world version of the "core staples" the city says it will make cheaper, which raises an obvious question: how do the neighborhood's stores compare to what a public store promises?

- Amazon + Whole Foods. In Jan 2026 Amazon said it would close its Amazon Fresh and Amazon Go stores, convert some to Whole Foods, open 100+ new Whole Foods, and lean hard into same-day fresh delivery. Amazon is now one of the top-three U.S. grocers, mostly online. This ties directly to (a) the Whole-Foods-in-Bushwick angle and (b) your delivery-app pricing decision.

- The inflation peg. Reporting points to NYC-metro food prices rising far faster than the national rate over the last decade. Find and cite the primary figures (e.g., the State Comptroller's food-price analysis) rather than repeating a number secondhand.

One angle to consider:  "We priced the basket the city wants to make cheaper, and here's what it actually costs across Bushwick right now." That ties your data to the municipal-grocery story. Test other angles too; the Pitch is where you argue for the best one.

# 7 · The Data-Collection System

You collect prices in the field on your phone through a Google Form. Each submission is one item at one store and writes a new row to the Price Data sheet in the Master Tracker, with your two photos attached. This keeps the data clean and lets the Editor watch progress live.

### The workflow in the store

- Open the Form on your phone (bookmark it to your home screen).

- For each basket item: find the item matching the locked spec, photograph the product, photograph the price tag, and enter the price + price type.

- Submit. Move to the next item. One submission = one item.

- That evening, open the Coverage Matrix tab to see which store × item cells are still empty.

### Build the Google Form (fields to create)

In the 04_Data_Collection folder: New, then Google Form. Turn ON "Collect email addresses" and, in Settings, allow file upload (this auto-saves photos to a Drive subfolder). Then set the response destination to a Sheet named Price Data and move/link it into the Tracker. Create these questions:

| # | Question | Type | Notes |
| --- | --- | --- | --- |
| 1 | Your name (collector) | Short answer / dropdown | Both interns' names |
| 2 | Store | Dropdown | Pre-load the locked store list |
| 3 | Store type / tier | Dropdown | Bodega / Discount / Mid / Premium-Natural / Produce-specialist / National chain / Delivery app |
| 4 | Date collected | Date | Required |
| 5 | Basket item | Dropdown | Pre-load the locked basket list |
| 6 | Brand found | Short answer | The actual brand on the shelf |
| 7 | Size / unit found | Short answer | e.g., 'half gallon', '1 lb', '12 ct' |
| 8 | Price ($) | Short answer | Number only, e.g., 3.49 |
| 9 | Price type | Multiple choice | Regular shelf / Sale / Loyalty / Unit price |
| 10 | In stock? | Multiple choice | Yes / Out of stock / Substituted |
| 11 | Product photo | File upload | 1 image |
| 12 | Price-tag photo | File upload | 1 image |
| 13 | Notes | Paragraph | Substitutions, oddities, anything unclear |

If a Form isn't practical:  you can enter rows straight into the Price Data tab on your phone and drop photos into the Photos subfolder using the naming convention Store_Item_type.jpg (e.g., KeyFood_Eggs_pricetag.jpg). The Form is smoother, but the sheet is the source of truth either way.

# 8 · Publish Checklist (Phase 9)

Run this before anything goes live. Check every box.

☐  Editor has given final approval on the draft.

☐  Every number in the story traces to a Price Data row (and a photo).

☐  A methodology box is included: what basket, which stores, which dates, and the limitations.

☐  Every quote is confirmed with the named source; spellings and titles correct.

☐  Store names and addresses double-checked against the store list.

☐  Charts (basket totals + index) and the store map are embedded and labeled.

☐  Photos are captioned and credited.

☐  Headline + dek finalized; SEO title/description set.

☐  Data-availability / source note included (consider linking the dataset like the 2021 piece did).

☐  Social posts + selfie videos ready and scheduled.

☐  Boost-account DMs drafted and ready to send after publish.

☐  Plan to monitor the first 48 hours for comments and corrections.

Then: publish the story, post the social package, send the boost DMs, then run the retro in 09_Publish_and_Handoff (what worked, what you'd change, what the data showed).

# 9 · Deliverable Index

Each phase has a template with fields. Here's where each lives and who signs off.

| Template | Folder | Sign-off |
| --- | --- | --- |
| Research Brief | 01_Research | Coordinator |
| Story Pitch | 02_Pitch | Editor |
| Methodology & Field Plan | 03_Methodology_and_Plan | Editor |
| Price Submission Form + Price Data sheet | 04_Data_Collection | Coordinator |
| Findings Memo | 05_Analysis_and_Findings | Coordinator |
| Source & Interview Log | 06_Reporting_and_Interviews | Coordinator |
| Article Draft | 07_Writing | Editor |
| Social & Promotion Package | 08_Social_and_Promotion | Editor |
| Master Tracker (all phases + basket + stores + data + analysis) | 00_START_HERE | shared |